AGENDA 8: Meeting Recommendations and Next Steps

On the Draft National and Regional TDA Reports

- Regional TDA/SAP Team (Liana) to provide the detailed monthly schedule, to be finalized and shared with RTF-EV team. PCU to provide the schedule in developing the SAP, to be shared after the meeting

- All technical comments should be submitted to PCU with copy to the regional TDA team, to be incorporated into the regional TDA report

On TDA transboundary problems and recommended national priorities and actions for CBA

- Synthesis of transboundary actions are initial blanket summary (based on the country priorities/presentations) that is subject for further improvement and revision including the titles (plus descriptions?)

- Regional TDA Team to provide the inputs needed like the final transboundary actions in two weeks, to start the EV work

- RTF EV members to provide and share ideas and inputs on CBA framework and guidelines with Dr. Luky

On achievement report and good practices documentation

- Country to provide additional inputs/updates on the draft achievement report on habitats in implementing the SAP within 2 weeks after the meeting

- Indonesia and Thailand (on LBP) to provide additional inputs/updates on good practices for online publication

- Tine to contact NTFP to provide the template and selection of outstanding good practices within 2 weeks (15 Feb) for storymap. Country to provide their inputs within a month after sharing the template